## Sheet1
Group Name | Team Members | March |  |  |  | April |  |  |  | May |  |  |  | June
|  | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | W1 | W2 | W3 | W4 | Notes
WP 1: LeadingGroup Manager: Xinyu Yao | 2
Task 1.1:Deciding the meeting-time and deadline of Weekly_Update.
Task 1.2:Deciding how to measure the project progress and makes the standard of weekly log.For example,record the amount of functions and methods which has been implemented.Writes the result on the Word document or Excel.
Task 1.3:Writes codes about program main functions.
Task 1.4:Evaluating the efficient of group progress and whether it can keep up with the goal.Decision what need to do if group progress is backward.Evaluating the quality of our program by using knowledge of methodology.
WP 2: CustomerGroup Manager: Xienan Wang | 2
Task 2.1:Determine the customer group and customer needs based on the known information of project (Healing Paws VeterinaryHospita)
Task 2.2: Design the relevant functionalities according to the customer group and needs
Task 2.3: Evaluate the designed functionalities (conduct customer surveys and modify the function design based on the feedback)
Task 2.4: Code the designed functionalities
Task 2.5 Test the program with the customers and improve the program according to the suggestions on revision of program
WP3: CodeGroup Manager: Xiulin Wu,Shiyuan Yang | 5 | [16 empty] | zzz
Task 3.1: Design the basic functions and determine the required technology | [17 empty] | zzz
Task 3.2: Establish basic structure, and Realize reservation function
Task 3.3: Implement advanced functionality
Task 3.4:Divide into two portals - one for customers and one for employees
Task 3.5 Test the functions and resolve errors.
Task 3.6 Combining all the sections and test the whole program
WP4: MaintenanceGroup Manager: Jiadi Li | 2 | [16 empty] | zzz
Task 4.1: Establish and maintain an cooperation work space,for example,hosting code on Github, organizing the documents and Github wiki. Design document standard and place the weekly progress with main targets on Readme file.
Task 4.2:Track the whole process and try to make recording in support with writing later technological document
Task 4.3: Work on solution in the server-side, being able to integrated with the upper layers(Code Division).Server-side program should be the major delivery of this group.
Task 4.4:Test delivery in the early stage of development. And also prepare for the user instruction in the end.
add or remove work packages and tasks as necessary | [14 empty] | Deliverable
Milestone